## Merit Project Communications
# | Communication | Medium | Delivery Date | Frequency | Description/Notes | Audience | Reviewer | Executives/Staff | Owner
1 | Project Team Communication | Meeting | Ongoing | Montly | Monthly meeting to discuss any issues regarding the current status of the overall project | High Ranking Executives (Project manager/Technical Manager/Etc) | Haziq | Executives | Nabil
2 | System Module Communication | Online Meeting | Ongoing | Weekly | Weekly status meeting regarding the system development (User Interface/Database/Etc) | System Developers | Nabil | Staff | Haziq
3 | AI Module Communication | Online Meeting | Ongoing | Weekly | Weekly status meeting regarding the system's AI development module (Natural Language Processing/Machine Learning/Etc) that will be implemented into the system | AI Developers | Nabil | Staff | Haziq
4 | Executive Sponsor Communication | PPT | Ongoing | Once per two weeks | Weekly status report to executive sponsors for overview of the project progress | Project's Sponsors | Naufal | Executives | Nur
5 | Sponsor's Contract | Online Meeting | Ongoing | Monthly | Discussion on how long the sponsor need to invest based on the project's progression | Project's Sponsors | Nur | Executives | Naufal
6 | Financial Management | Letter | Ongoing | Monthly | Report on the total money spent on the project | Financial Analyst, Executive Sponsors | Naufal | Executives | Nur
7 | Company member roles & responsibility | Email | 2020-09-13 | Monthly | Create list of responsibilities for member (e.g. communicate appropriate information to supevisors, dept heads, AVP's etc.) | Company Members | Nabil | Staff | Naufal
8 | Communication to departments regarding overall performance | Email | 2020-09-15 | Monthly | Will include instructions on ways to notify employees. | Head of Department | Nur | Executives | Haziq
9 | Project Review | Meeting | - | At milestones | Present project deliverables, gather feedback, and discuss future project enhancement | Company Members, Project's Sponsors | Nabil | Staff | Haziq
10 | Project Status Report | Email | Ongoing | Daily | Report the status of the project including activities, progress, costs, and issues | Project's Sponsors, Company Members | Nur | Staff | Haziq
11 | Post-mortem meetings | Online Meeting | 2021-01-08 | At the end of project | Assess what worked and what did not work and discuss actionable takeaways | Company Members | Nur | Staff | Haziq