## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART: LYRICBOT INC
PROJECT TITLE | Lyric Bot
PROJECT MANAGER | ABDUL HAZIQ BIN ABD KHALID
COMPANY NAME | Lyric Bot Sdn. Bhd.
DATE | 2020-12-10 | [5 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Inititation
1.1 | Project Charter | Naufal | 2020-12-10 | 13/10/2020 | 1 | 100%
1.1.1 | Research | Nabil | 2020-12-10 | 13/10/2020 | 1 | 100%
1.2 | Projections | Md Nur | 13/10/2020 | 14/10/2020 | 1 | 100%
1.3 | Stakeholders | Naufal | 15/10/2020 | 18/10/2020 | 3 | 100%
1.4 | Guidelines | Haziq | 16/10/2020 | 18/10/2020 | 2 | 100%
1.5 | Project Inititation | Md Nur | 19/10/2020 | 19/10/2020 | 1 | 100%
2 | Project Planning & Scope
2.1 | Collect Requirement | Nabil | 20/10/2020 | 21/10/2020 | 1 | 100%
2.2 | Scope & Goal Setting | Haziq | 20/10/2020 | 21/10/2020 | 1 | 100%
2.3 | Create WBS | Naufal | 22/10/2020 | 25/10/2020 | 3 | 100%
2.4 | Verify Scope | Haziq | 26/10/2020 | 29/10/2020 | 3 | 100%
2.5 | Control Scope | Nabil | 30/10/2020 | 2020-03-11 | 3 | 100%
2.6 | Investment Planing | Md Nur | 2020-05-11 | 2020-07-11 | 3 | 100%