## Consolidated RAM
Resource Responsibility P - Primary Responsibility A - Approval Authority S - Supporting Responsibility (Contributor or Reviewer) I - Information Only (Select from drop down list) | Project Director | Project Manager | Risk Manager | Financial Analyst | Contract Manager | Quality Manager | Technical Manager | System Engineer | Implementation Manager | Web Support Manager | Test Manager | Configuration Manager | Operations Manager | Customer Support Manager | Project Sponsor
Project Funding
Budget Estimation | A | A | P | P | S | I | I | I | I | I | I | I | I | I | A
Securing Sponsor | A | S | S | S | P | I | I | I | I | I | I | I | I | I | I
Fund Negotiation & Agreement | A | A | S | S | P | I | I | I | I | I | I | I | I | I | A
Financial Management | A | S | S | P | I | I | I | I | I | I | I | I | I | I | A
Acquisition Planning | bar: A A A A
Statement of Need | A | P | S | S | P | I | S | S | I | I | I | I | S | I | I
Cost Handling | A | A | S | P | P | I | I | I | I | I | I | I | I | I | A
Risks | A | A | P | S | P | I | I | I | I | I | I | I | I | I | I
Trade-offs | A | A | P | S | P | I | I | I | I | I | I | I | I | I | I
Contracting | bar: A A A A
Intellectual Property | A | A | I | I | P | I | I | I | I | I | I | I | I | I | S
Product Licences | A | A | S | S | P | I | I | S | I | I | S | I | I | I | I
Fund Agreement | A | A | S | P | P | I | I | I | I | I | I | I | I | I | A
Design Pattern | A | A | I | S | P | I | I | I | I | I | I | I | I | I | A
Employment Contract | A | A | S | P | P | S | S | S | S | S | S | S | S | S | I
Requirements Analysis | bar: A A A A A
System Requirement | A | P | S | S | I | P | I | P | I | I | I | S | I | I | I
Business Requirement | A | P | I | P | S | I | I | I | I | I | I | I | I | I | A
User/Stakeholder Requirement | A | P | I | I | P | I | I | I | I | I | I | I | I | S | S
Implementation Requirement | A | P | I | S | I | S | I | S | P | S | S | I | S | I | I
Functional Requirement | A | P | I | I | I | S | I | I | S | I | I | S | P | I | I
Non-Functional Requirement | A | P | I | I | I | S | I | I | S | I | I | S | P | I | I
System Design | bar: A A A A A A
System Architecture | A | S | I | I | I | I | I | P | S | S | I | I | I | I | I
User Interface | A | S | I | I | I | I | I | P | S | S | I | I | I | I | I
Database Design | A | S | I | I | I | I | I | P | S | S | I | I | I | I | I
System Development | bar: A A A
Coding | A | I | I | I | I | I | I | P | I | S | I | I | I | I | I
Debugging | A | I | I | I | I | I | I | P | I | S | I | I | I | I | I
System Implementation | bar: A A
Acceptance Testing | A | S | I | I | P | S | I | I | P | I | P | I | I | I | I
Problem Handling | A | P | P | I | I | S | P | P | P | I | P | S | I | I | I
Monitoring and Control | A | S | P | I | I | S | S | P | P | I | P | S | I | I | I
Functional Testing | A | S | I | I | I | S | P | P | P | I | P | S | I | I | I
Resources
P
A
S
I