## TIME MANAGEME Gantt Chart BLANK
TIME MANAGEMENT GANTT CHART TEMPLATE
[Lyric Bot ]
TASK NAME | START DATE | END DATE | DURATION (days)
Project Initiation | 2020-10-12 | 2020-10-19 | 8
Project Planning & Scope | 2020-10-20 | 2020-11-03 | 15
Budget & Cost Estimation | 2020-11-04 | 2020-11-09 | 6
AI System Design | 2020-11-10 | 2020-11-14 | 5
AI System Building | 2020-11-15 | 2020-12-02 | 18
Website Design | 2020-12-03 | 2020-12-05 | 3
Website Building | 2020-12-06 | 2020-12-22 | 17
Embedding system into website | 2020-12-23 | 2021-01-02 | 11
System Testing | 2021-01-03 | 2021-01-10 | 8
System Deployment | 2021-01-11 | 2021-01-19 | 9
Documentation | 2021-01-20 | 2021-01-22 | 3
MILESTONE 2:
14/11/20
Methodology and Analysis Phase
MILESTONE 3:
22/12/20
Module Design and Implementation Phase
MILESTONE 5:
22/01/21
System Demonstration
MILESTONE 4:
10/01/21
Module Integration and Testing Phase
MILESTONE 1:
19/10/20
Proposal Discussion and Verification